## Sheet1
Risk Id Numbers | 17
System Affected | Customer Service Portal
Organization Or Business Unit | Northeast Region Support Center
Risk Scenario Description | A natural disaster disrupts communications circuits impeding customer access.
Assets Affected | DMZ Router; Core_Switch_1; Fiber_Circuit_Bldg3_to_HQ;
Threat Source Actors | Natural Disaster - Hurricane
Threat Vectors | Physical Connectivity Disruption
Threat Events
Vulnerability Predisposing Conditions | Outdoor/Exposed Infrastructure
Primary Adverse Impact | Loss of communications to communcations center
Secondary Adverse Impacts | Customers unable to access service portal may be disgruntled; SLAs may be jeopardized
Other Scenario Details | Not Applicable
Risk Category | Contingency Planning
Likelihood Before Controls | 0.1
Impact Before Controls | 1500000
Exposure Rating Before Controls | 150000
Planned Risk Response | ['Mitigate']
Planned Risk Response Description | Having identified that the key vulnerability is to overhead communications wiring, these circuits will be buried underground.
Resource Requirements For Planned Risk | Network architecture staff to plan and design the new infrastructure (existing labor budget). Contract to install underground fiber-optic cabling between headquarters and the communications center including necessary permits, trench construction, conduit materials, and new communications equipment.
Planned Response Cost | 250000
Likelihood After Controls Will Be | 0
Impact After Controls | 1500000
Expected Exposure Rating | 0
Actual Response Cost | 245000
Likelihood After Controls Are In Place Will Be | 0
Impact After Controls Are In Place | 1500000
Final Exposure Rating | 0
Risk Owner Point Of Contact | Mark Winters <WintersMX@example.com>
Date Of Risk Identification | 2021-03-20
Source Of Risk Information | Contingency Planning Annual Exercise
Current Status Date | 2021-04-15
Dependencies | Availability of Construction Contractor
Follow Up Date | 2021-05-31
Comments | Still need to evaluate other potential issues from natural disasters (e.g., flooding) that may impact this system.