## Risk Register
Risk Id | Risk Description | Risk Category | Risk Likelihood | Risk Impact | Exposure Rating | Risk Response Type | Risk Response Cost | Risk Response Description | Risk Owner Point Of Contact | Status
| External thief steals a PC tower from the reception area | Physical and Environmental Protection (PE) | 0.75 | 0.1 | 7.5% (Low) | Accept | 0 | None required | Kira Caldwell | Open
| External malicious actor delploys a ransomware attack causing unavailability of financial systems | Systems and Information Integrity (IS) | 0.9 | 0.9 | 80% (High) | Mitigate | 3700000 | Segment internal networks (AC-4, NIST CSF PR.AC-5) Improve backup plans (CP-9, NIST CSF PR.IP-4) | Jemima Daugherty Carly Hickman (backup) | Open
| A natural disaster disrupts communications circuits impeding customer access | Contingency Planning (CP) | 0.4 | 0.3 | 12% (Low) | Transfer | 125000 | Purchase cybersecurity insurance to reimburse downtime | Mark Winters | Closed
| Human Resource Management Systems move to a cloud solution provides in-house IT infrastructure savings and improves availability | System and Services Acquisition (SA) | 0.5 | 0.5 | 25% (Moderate) | Realize | 2000000 | Conduct mitigation to SaaS provider Confirm system reliability Decommision HR Minicomputer | Amir Marsh | Open
| Portable workstation containing digital desigs is lost (e.g. left on an airplane) | System and Comm. Protection (SC) | 0.8 | 0.7 | 56% (Moderate) | Mitigate | 275000 | Implement full-disk encryption of sensitive devices (SC-28, NIST CSF PR.DS-1) Implement remote tracking and ensure solution (MP-6, NIST CSF PR.DS-1) | Jeffrey Contreras | Updated